## Simple Gantt Chart - EX
SIMPLE GANTT CHART TEMPLATE
PROJECT TITLE
PROJECT MANAGER
COMPANY NAME
DATE
[22 empty] | PHASE TWO | [29 empty] | PHASE FOUR
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Project Charter | Leon W | 2023-03-12 | 2023-03-15 | 3 | 100%
1.1.1 | Project Charter Revisions | Kylie R | 2023-03-15 | 2023-03-16 | 1 | 100%
1.2 | Research | Pete S | 2023-03-15 | 2023-03-21 | 6 | 90%
1.3 | Projections | Steve L | 2023-03-16 | 2023-03-22 | 6 | 40%
1.4 | Stakeholders | Allen W | 2023-03-17 | 2023-03-22 | 5 | 70%
1.5 | Guidelines | Malik M | 2023-03-18 | 2023-03-22 | 4 | 60%
1.6 | Project Initiation | Malik M | 2023-03-23 | 2023-03-23 |  | 50%
2 | Project Definition and Planning
2.1 | Scope and Goal Setting | Steve L | 2023-03-24 | 2023-03-28 | 4 | 5%
2.2 | Budget | Allen W | 2023-03-29 | 2023-04-02 | 4 | 30%
2.3 | Communication Plan | Malik M |  |  |  | 0%
2.4 | Risk Management | Malik M |  |  |  | 0%
3 | Project Launch and Execution
3.1 | Status and Tracking | Pete S |  |  |  | 0%
3.2 | KPIs | Leon W |  |  |  | 0%
3.2.1 | Monitoring | Kylie R |  |  |  | 0%
3.2.2 | Forecasts | Kylie R |  |  |  | 0%
3.3 | Project Updates | Pete S |  |  |  | 0%
3.3.1 | Chart Updates | Malik M |  |  |  | 0%
4 | Project Performance / Monitoring
4.1 | Project Objectives | Steve L |  |  |  | 0%
4.2 | Quality Deliverables | Allen W |  |  |  | 0%
4.3 | Effort and Cost Tracking | Malik M |  |  |  | 0%
4.4 | Project Performance | Malik M |  |  |  | 0%
CLICK HERE TO CREATE IN SMARTSHEET

## Simple Gantt Chart - BLANK
TÂCHES ET DATES | SEPTEMBRE |  |  |  |  | SEPTEMBRE |  |  |  |  | SEPTEMBRE |  |  |  |  | SEPTEMBRE |  |  |  |  | SEPTEMBRE |  |  |  |  | SEPTEMBRE
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Dates clés
Attribution du sujet
Rapport d'analyse
Rapport final
Soutenance
Examens
Tâches
Conception diagrammes UML
Rédaction dossier d'Analyse
Création de la BDD
Création de l'API
Fonctionnalité(s)
Fonctionnalité(s)
Fonctionnalité(s)
TÂCHES ET DATES | OCTOBRE |  |  |  |  | OCTOBRE |  |  |  |  | OCTOBRE |  |  |  |  | OCTOBRE |  |  |  |  | OCTOBRE |  |  |  |  | OCTOBRE
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 30
Dates clés
Attribution du sujet
Rapport d'analyse
Rapport final
Soutenance
Examens
Tâches
Conception diagrammes UML
Rédaction dossier d'Analyse
Création de la BDD
Création de l'API
Fonctionnalité(s)
Fonctionnalité(s)
TÂCHES ET DATES | NOVEMBRE |  |  |  |  | NOVEMBRE |  |  |  |  | NOVEMBRE |  |  |  |  | NOVEMBRE |  |  |  |  | NOVEMBRE |  |  |  |  | NOVEMBRE
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Dates clés
Vacances
Rapport d'analyse
Rapport final
Soutenance
Examens
Tâches
Conception diagrammes UML
Rédaction dossier d'Analyse
Création de la BDD
Création de l'API
Fonctionnalité(s)
Fonctionnalité(s)
TÂCHES ET DATES | DECEMBRE |  |  |  |  | DECEMBRE |  |  |  |  | DECEMBRE |  |  |  |  | DECEMBRE |  |  |  |  | DECEMBRE |  |  |  |  | DECEMBRE
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Dates clés
Vacances
Rapport d'analyse
Rapport final
Soutenance
Examens
Tâches
Conception diagrammes UML
Rédaction dossier d'Analyse
Création de la BDD
Création de l'API
Fonctionnalité(s)
Fonctionnalité(s)

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.